Backlog Review Summary

Although the backlog contains stories, some of them have issues.

Unclear stories: “Tasks saved automatically” and “Dashboard” are vague and could mean multiple things (auto-save timing, offline, UI layout, analytics).

Oversized story: “User profile management” bundles multiple capabilities (view profile, edit profile, password changes) and is too large for a single sprint.

Missing acceptance criteria: Several items lack testable conditions (e.g., “Search/filter tasks,” “Priority levels”).

Sequencing issues: “Search/filter” and “Dashboard” should not be prioritized ahead of core CRUD + authentication; “Persistent storage” must come before many user-facing flows.

Refined Backlog Items (Rewrite 4+ items, split oversized)

Refined Item 1 - Tasks saved automatically

As a user, I want my tasks saved to the database when I create, update, or delete them so that my changes persist after refreshing or logging out.

This now defines triggers like create/update/delete and measurable outcome (persists after refresh/logout).

Refined Item 2 - Create Dashboard Interface

As a user, I want a task dashboard that displays my tasks grouped by status (To Do/Doing/Done) so that I can see progress at a glance.

Clarifies and separates the features that are useful and included in creating the dashboard.

Refined Item 3 -  Search/filter tasks

As a user, I want to search tasks by keyword in the title so that I can quickly find a specific task.

Narrows scope to searchable field and gives testable behavior.

Refined Item 4 - User profile management

As a user, I want to view my profile details so that I can confirm my account information.

As a user, I want to update my profile details so that my account information stays current.

Profile management contains multiple user flows and validations; splitting makes stories small, estimable, and testable.

Estimation

Story Point Estimates

| Story | Backlog Item (Refined) | Points | Estimation Notes |
| --- | --- | --- | --- |
| 1 | Create account | 5 | DB write, validation, security considerations |
| 2 | Log in | 3 | Auth logic, token/session handling |
| 3 | Create task | 3 | CRUD endpoint, DB insert |
| 4 | View task list | 3 | Query, response shaping |
| 5 | Update task status | 3 | Update endpoint, validation of allowed statuses |
| 6 | Persist changes on create/update/delete | 5 | Cross-cutting persistence expectations across multiple flows |
| 7 | Task priority levels | 3 | Add field, UI control, validation |
| 8 | Due dates | 3 | Add field, date validation, display |
| 9 | View profile | 2 | Simple read/display |
| 10 | Update profile | 3 | Update flow, validation |

Reprioritization Rationale (Reordered Backlog)

Prioritization is driven by:

- Business value (MVP): users must authenticate and manage tasks

- Dependencies: tasks depend on auth; enhancements depend on CRUD

- Risk reduction: persistence and core flows validated before “nice-to-haves”

Reordered Backlog (Top → Bottom)

- Create account: Required for secure access

- Log in: Required for user-specific data

- Create task: Core value

- View task list: Core value + validation of storage

- Update task status: Core progress tracking

- Persist changes reliably: Reduces data loss risk, stabilizes MVP

- Priority levels: Enhances planning, depends on task model

- Due dates: Enhances planning, depends on task model

- View profile: Non-core

- Update profile: Non-core + extra validation

This order provides a working product early for a strong foundation then adds extras later.

Dependency and Risk Notes

Dependencies

Auth dependency: Story 2 depends on Story 1.
User cannot save information such as login without authentication, so create account comes first.

Task dependency: Stories 7 and 8 depend on stories 3 and 4
Extra task features are not valuable until tasks can be created and viewed.

Risks

Integration risk: If UI expects a task shape, API might return something different.
This would require devs to go back and change shapes wherever needed, so it is important to create core features first to get a consistent shape first to mitigate this issue later.

Security risk: Users could access other users’ tasks if authorization checks are missing. Need early attention to login and authentication processes and task writes to ensure they are individual and secured.