Sprint Goal

The goal of this sprint is to create a backend and core functionalities for the task list app. The sprint will develop the database, login, and main task features like delete and create. This will become the most basic foundation that can show a working product at the end of the sprint.

Selected Backlog Items

Story 1: User Login System - 3 Story Points
Users can securely log in to access their data.
Authentication is required before implementing secure task ownership and access.

Story 2: Create Task - 3 Story Points
Users can create and save new tasks in the system.
Task creation is core functionality and provides immediate business value.

Story 3: Delete Task - 3 Story Points
Users can delete tasks they no longer need.
Task deletion is a core functionality and provides immediate business value.

Story 4: Persistent Database Storage - 5 Story Points
Tasks and user data are stored permanently in the database.
Persistence is required to ensure data reliability and enable full application functionality.

Story 5: Update Task Status - 3 Story Points
Users can update task status (To Do, Doing, Done).
Enables task progress tracking, completing core task management functionality.

Task Breakdown

Story 1: User Login System

Task 1: Implement login API endpoint – Backend – 6 hours
Task 2: Implement authentication logic and validation – Backend – 6 hours
Task 3: Test login functionality and error handling – QA – 4 hours
Total: 16 hours

Story 2: Create Task

Task 1: Create task database schema and model – Backend – 5 hours
Task 2: Implement task creation API endpoint – Backend – 6 hours
Task 3: Test task creation functionality – QA – 3 hours

Total: 14 hours

Story 3: Delete Task

Task 1: Create task database schema and model – Backend – 5 hours
Task 2: Implement task deletion API endpoint – Backend – 6 hours
Task 3: Test task deletion functionality – QA – 3 hours
Total: 12 hours

Story 4: Persistent Database Storage

Task 1: Configure database connection – Backend – 6 hours
Task 2: Implement data persistence logic – Backend – 6 hours
Task 3: Verify persistence through testing – QA – 4 hours
Total: 16 hours

Story 5: Update Task Status

Task 1: Implement status update API endpoint – Backend – 5 hours
Task 2: Connect update logic to database – Backend – 4 hours
Task 3: Test status update functionality – QA – 3 hours
Total: 12 hours

Capacity and Feasibility

There is a team of 5 with one PO, one Scrum Leader, and 3 developers who make code and test. Each developer dedicates about 7 hours a day which becomes about 70 hours a person over a 2 week period. That is 210 hours as compared to the total work of the stories which is only 70 hours, so the team will spend about 33% of its time building the product which leaves 67% to testing and sanity checking.

Sprint Execution Plan

Every day of the workweek, the Scrum Master will hold a daily scrum to ensure the dev team is properly able to continue with their work and coordinate the tasks accomplished by each member and what they are looking forward to completing. At the end of the sprint, the team will get together to review the final product they have created for that sprint cycle to show and get feedback on, then go through a sprint retrospective to evaluate how the team had performed and identify what was done well and what could have been better.

If the scope changes in the middle of the sprint, then the Product Owner should try to include it in the product backlog for the next sprint cycle unless it is absolutely critical.